## 0 · Start Here
LUMENWRIGHT — MASTER BUSINESS PLAN
The Light Atelier: custom lighting installations · vintage rehabilitation · rare chandelier repair · turnkey LED retrofit · Vela Series proprietary LED · AI Lighting Studio · Designer Network
Prepared July 7, 2026 · Living document — every number is an editable assumption, not a promise
HOW TO USE THIS WORKBOOK
1 · Business Plan | The full plan: market, customers, competition, operations, team, risk. Read first.
2 · GTM + Workback | Go-to-market strategy and the dated week-by-week workback schedule to the Oct 1, 2026 launch.
3 · Phased Approach | Five phases from foundation to scale, each with entry/exit gates. Don't skip gates.
4 · Revenue Engine | How every dollar is made: six streams, unit economics, pricing, LTV/CAC, cash cycle.
5 · Forecast | 36-month financial model with live formulas. Change the yellow assumption cells; everything recalculates.
6 · Designer Network | The supply side: recruiting, vetting, economics, and scaling the designer partner network.
7 · Digital Marketing | SEO, content, social strategy by platform, paid media, email, and the 12-week launch calendar.
8 · Vendors + Sourcing | Who actually makes and supplies everything — named suppliers, sourcing process, vetting checklist.
9 · Funding + Startup Costs | Itemized startup budget and the SBA-anchored funding stack, with lender requirements.
THE TEN NUMBERS THAT MATTER
# | Metric | Target | Why it matters
1 | Launch date | Oct 1, 2026 | Everything in the workback drives to this
2 | Startup capital required | $118,500 | See Funding tab — funded by ~$18.5k owner + ~$100k SBA
3 | Lighthouse projects (Phase 1) | 10 by Mar 2027 | Case studies are the marketing engine; nothing scales without them
4 | Year 1 revenue (conservative) | ≈$380,000 | Forecast tab base case — edit the yellow cells to make it yours
5 | Blended gross margin | ≥45% | Below 40% = pricing problem; fix before scaling
6 | Cash-flow breakeven | Month 10–12 | Made-to-order deposits make this achievable
7 | Founding designers signed | 8 by Dec 2026 | Network gate for Phase 2
8 | AI Studio → consult conversion | ≥8% | The funnel's core efficiency metric
9 | Customer acquisition cost | ≤$450 residential / ≤$1,200 commercial | Payback in first project or the channel is off
10 | 5-yr service plan attach rate | 100% of turnkey projects | This is the moat and the recurring revenue base
OPERATING PRINCIPLES
1. Deposits before parts — 50% on order, made-to-order only. Working capital stays positive.
2. No claim we can't defend — licensing, savings math, and lead times are stated exactly.
3. Every project produces an asset — photos, a case study, a review, a referral ask. No exceptions.
4. The AI studio is a funnel, not a product. A human closes every deal.
5. Retrofit pays the bills; restoration builds the brand; Vela builds the equity.

## 1 · Business Plan
1 · THE BUSINESS PLAN
1.1 COMPANY OVERVIEW
Legal form | Single-member LLC (elect S-corp at ~$60k+ owner pay); registered in home state; DBA 'Lumenwright'
What we do | One studio for the full life of light: design + build custom fixtures, restore vintage/rare fixtures, repair chandeliers, and convert buildings to LED under a turnkey program with 5 years of included service
Vertically integrated model | Design → specification → procurement (manufacturer partners) → delivery → installation (licensed partner/staff) → 5-yr service. One accountable party.
Proprietary product | Vela Series architectural LED line (channel, downlight, cove, façade, controls) — third-party manufactured, spec'd through our projects first, sold to trade second
Technology edge | AI Lighting Studio: photo → personalized 3-layer lighting plan → designer-reviewed consult. 24/7 lead qualification no competitor in the niche has.
Assets already built | Live website (Next.js/Vercel), Supabase operations database (catalog, orders, leads, referrals), designer network infrastructure, AI analysis pipeline
1.2 THE PROBLEM
Homeowners/designers with vintage fixtures have almost nowhere to take them — electricians won't touch crystal, and restorers won't touch wiring.
Small/mid commercial buildings overpay for lighting energy because national ESCOs ignore projects under ~$250k and electricians sell hardware, not outcomes (no audit, no rebate filing, no service).
Design-driven clients can't buy 'one accountable party' — they assemble designer + showroom + electrician + handyman and absorb the seams.
Independent lighting designers lose projects because they lack fabrication, product margin, and installation muscle behind them.
1.3 MARKET (estimates — validate locally in Phase 0)
Segment | Size signal | Our slice (SOM logic)
US lighting fixtures market | ≈$30B+ annual, LED share still growing | We are not chasing share; we are extracting high-margin niches
Commercial LED retrofit services | Tens of $B remaining conversion backlog; ~half of US commercial floorspace still has fluorescent/HID | Local SMB buildings 10k–100k sq ft: offices, gyms, warehouses, churches, retail
Lighting restoration/repair | Fragmented cottage industry; no dominant brand; strong search demand, thin supply | Regional monopoly potential within 12–18 months; national via ship-in commissions
Custom/decorative fixtures | Growing 'quiet luxury' + hospitality refresh cycles | 5–15 statement pieces/yr at $5k–$15k+ each via designers
Architectural LED (Vela) | Spec-driven; wins compound via designer relationships | Attach to every project yr 1; third-party spec sales yr 2+
SOM sanity check: Year-1 plan requires ~2 retrofit projects + ~3 restorations + ~1 custom piece per month by month 12 in ONE metro. That is a rounding error of local demand.
1.4 CUSTOMER SEGMENTS (ICPs)
ICP | Profile | Trigger moment | What they buy first | Avg first ticket
Heritage Homeowner | Owns pre-1960 home or inherited fixtures; 45–75; values provenance | Estate inheritance, renovation, a dead chandelier | Restoration commission / relamp set | $1,500–$6,000
Design-Led Renovator | 35–60, $150k+ HHI, working with (or wanting) a designer | Kitchen/whole-home reno; saw a photo they loved | AI plan → custom pendant/chandelier package | $3,000–$12,000
SMB Owner-Operator | Owns/controls building 10k–60k sq ft; pays own utility bill | Utility bill spike; ballast failures; rebate deadline | Free audit → turnkey retrofit | $15,000–$60,000
Hospitality Operator | Restaurant/boutique hotel, 1–5 locations | Opening, refresh, or 'the room feels wrong' | Design consult → feature fixtures + scenes | $10,000–$40,000
Trade Partner (designer/architect/GC) | Specs lighting but can't fabricate/install/service | A project they can't staff | Network membership → spec support + product | $2,000–$20,000/project
1.5 COMPETITION & POSITIONING
Competitor type | Their strength | Their gap | Our counter
National ESCOs (retrofit) | Scale, financing | Ignore sub-$250k projects; no design sensibility | Turnkey for SMB; design-grade light quality; 5-yr service
Electrical contractors | Licensed, local, trusted | Sell hardware not outcomes; no audits/rebates/design | We hand them work (network) instead of fighting them
Lighting showrooms | Product selection | No install, no custom, no service; margin-squeezed by e-comm | Made-to-order + install + service; showrooms can become partners
Etsy/antique restorers | Craft credibility | No electrical compliance, no scale, no warranty | Code-compliant restoration + dossier + 5-yr warranty
Online fixture retailers | Price, breadth | Zero service; commodity product | We don't compete on price; we sell finished outcomes
Positioning statement | For people and businesses who care what light does to a space, Lumenwright is the only studio that designs, builds, restores, converts, and then services light for five years — one accountable partner from photo to finished room.
1.6 OPERATIONS PLAN
Area | Plan | Cost reference (Funding tab)
Facility | Phase 0–1: home workshop/garage + storage unit for crating. Phase 2: 1,200–2,000 sq ft light-industrial bay (~$1,500–2,500/mo) with bench, spray/patina area, photo corner | Facility line
Licensing (CRITICAL PATH) | Do not advertise installation until solved. Options: (a) subcontract to licensed EC under written agreement — fastest, do this first; (b) hire licensed journeyman month 7–9; (c) owner pursues license long-term. Restoration bench work + retrofit kit supply are legal without EC license in most states — verify with state board in week 1. | Legal/licensing line
Insurance | GL $1M/$2M + products/completed ops; inland marine for client fixtures in shop (restoration!); commercial auto; workers comp at first hire; E&O once designing for trade | Insurance line
Equipment | Restoration bench (rewiring, plating prep, crystal pinning), test rig (dimmer wall!), crating station, van (used, wrapped) | Equipment lines
Compliance | Old lamp/ballast disposal = EPA Universal Waste rules — contract a certified recycler (e.g., national mail-back programs) and keep manifests; it's a selling point, not just a cost | Ops line
Software stack | Site+DB built ($0); add: QuickBooks, Jobber/ServiceTitan-lite for field, Stripe/Shopify when payments go live | Software line
1.7 TEAM & HIRING PLAN
When | Role | Type | Comp target | Trigger
Now | Founder — design, sales, bench, everything | Owner | $3–4k/mo draw until M6, then $6k | —
M3–M6 | Licensed electrical sub (per-project) | 1099/sub | 15–22% of install labor line | First install sold
M7–M9 | Restoration/bench tech (craft hands) | PT→FT | $22–28/hr | Bench backlog > 3 weeks
M9–M12 | Licensed journeyman electrician | FT | $70–90k + van | ≥2 retrofits/mo for 3 straight months
M12–M18 | Ops/project coordinator | FT | $50–60k | Founder >30% time on scheduling
M18+ | Second crew / designer-in-residence | FT | Market | Phase 3 gates met
1.8 RISK REGISTER
Risk | Likelihood | Impact | Mitigation
Licensing/regulatory misstep | Med | High | Sub-first model; state board verification in writing; never advertise beyond scope
Founder capacity (everything on one person) | High | High | Ruthless phase gates; sub/PT help early; the workback has slack built in
Retrofit price competition | Med | Med | Compete on turnkey outcome + service, never on $/fixture; walk from bid wars
Vela ODM quality failure | Med | High | Third-party inspection every PO; LM-79/80 reports; dual-source by yr 2; never spec into a project without stock on hand
A damaged heirloom in our care | Low | Severe | Inland marine insurance; intake condition documentation (photo+video); conservative promise-making
Utility rebate program changes | Med | Med | Rebates framed as bonus not basis; track programs quarterly; diversify streams
Cash crunch from growth | Med | High | 50% deposits; CAPLine/LOC in place BEFORE needed (Funding tab); weekly 13-week cash forecast
Designer network conflict (channel vs direct) | Low | Med | Clear rules of engagement in founding-member agreement; designers always own the client they bring
1.9 KPIs — REVIEWED WEEKLY
Funnel | Economics | Delivery | Brand
Site visits · AI plans run · consults booked · close rate | GM% by stream · CAC by channel · payback (days) · cash weeks on hand | On-time delivery % · punch-list items/project · service response hrs | Reviews (count/rating) · case studies published · designer NPS

## 2 · GTM + Workback
2 · GO-TO-MARKET + WORKBACK SCHEDULE
2.1 GTM STRATEGY IN ONE PARAGRAPH
Launch Oct 1, 2026 in ONE metro with two spearheads: (1) the Founding Client Program — 10 lighthouse projects sold at cost-plus in exchange for full case-study rights, reviews, and referrals; (2) the free commercial lighting audit, pitched直direct to 100 hand-picked SMB buildings. The AI Studio is the top of funnel for everything; every plan ends in a human consult. Designers are recruited in parallel (tab 6) so that by Phase 2 the network is a second sales force. We do not do broad paid media until case studies exist.
2.2 OFFER LADDER (how strangers become $40k clients)
Step | Offer | Price | Purpose
1 | AI Lighting Plan (photo → plan) | Free | Capture + qualify; deliver instant value
2 | Designer review call (20 min) | Free | Human trust; scope the real project
3 | Paid design consult / commercial audit | $150–$500 (credited to project) | Commitment filter; audit produces the savings analysis
4 | Project (restore / custom / retrofit) | $1.5k–$60k | Core revenue
5 | 5-yr service plan (turnkey: included) | Included / $29–99/mo standalone | Retention moat + recurring base
2.3 CHANNEL PRIORITY (first 6 months)
Rank | Channel | Target | Why now
1 | Founding Client Program (direct outreach + personal network) | 10 projects by Mar | Case studies before ad spend
2 | Direct commercial outreach (100-building list) | 20 audits, 6 conversions | Highest ticket, controllable
3 | Google Business Profile + local SEO | Top-3 map pack for 'chandelier repair <metro>' | Restoration demand already searches; low competition
4 | Designer/trade recruitment | 8 founding members | Compounding channel
5 | Organic social (restoration content) | Content bank of 30 posts | Feeds everything later; near-zero cost now
Hold | Paid search/social | Start M4+ only after 5 case studies | Ads amplify proof; they don't create it
2.4 WORKBACK SCHEDULE — TO OCT 1, 2026 LAUNCH (today = Jul 7)
Week of | Workstream | Deliverable (done = shippable) | Owner
Jul 7 | Legal/Compliance | LLC filed; EIN; state electrical-board scope ruling requested IN WRITING; insurance quotes ordered | Founder
Jul 7 | Funding | SBA package started: this workbook + personal financial stmt; 3 lender/CDFI intros requested (Lender Match) | Founder
Jul 14 | Ops | GL + inland marine bound; lamp-recycler contract signed; bench equipment ordered | Founder
Jul 14 | Product | Vela ODM shortlist (5 candidates) contacted; sample POs for Linea + Punto; retrofit kit distributor accounts opened (2 min.) | Founder
Jul 21 | Brand/Site | Real business name/entity decision locked; site lib/site.ts updated (name, inboxes, credentials); domain purchased + connected on Vercel | Founder
Jul 21 | Sales assets | Commercial audit one-pager; restoration intake form; founding-client agreement drafted | Founder
Jul 28 | Licensing | Electrical sub agreement signed with 1–2 licensed ECs (rate card + insurance certs on file) | Founder
Jul 28 | Network | Designer prospect list built (50 names: IALD/ALA/IES rosters + IG); outreach sequence written | Founder
Aug 4 | Founding clients | Founding Client Program page live; 25 personal-network invitations sent; 100-building commercial list built (county records + walk-the-street) | Founder
Aug 4 | Content | First restoration documented start-to-finish (own/thrifted fixture if no client yet) — 200+ photos, video | Founder
Aug 11 | Product | Vela samples received → test rig validation (dimming curves, CCT, flicker); accept/reject; production PO for launch stock | Founder
Aug 11 | Sales | First 3 founding projects signed (any mix); first commercial audits booked (target 5) | Founder
Aug 18 | Marketing | GBP live + 10 photos; local citations (top 20 directories); review flow tested end-to-end | Founder
Aug 18 | Ops | Supabase order/lead pipeline drilled: order → confirm → manufacturer PO → delivery → service record. Test with founding project #1 | Founder
Aug 25 | Funding | SBA application submitted (microloan or 7(a) small per Funding tab decision) | Founder
Aug 25 | Content | Case study #1 published (site + GBP + social); email sequence for AI-plan leads written (5 emails) | Founder
Sep 1 | Sales | Founding projects 4–6 signed; 2 retrofit audits delivered with savings analysis; first retrofit proposal out | Founder
Sep 8 | Network | First 3 designer applications through vetting; founding-member terms finalized from their feedback | Founder
Sep 8 | Site | Payments decision executed (Stripe deposits recommended); env vars set; live order flow tested with real card | Founder
Sep 15 | Marketing | Launch content batch produced: 12 posts scheduled, launch email written, PR pitch to 5 local outlets ('the chandelier surgeon' angle) | Founder
Sep 22 | Dress rehearsal | Full dry run: AI plan → consult → proposal → deposit on a real prospect; fix every seam found | Founder
Sep 29 | LAUNCH WEEK | Public launch Oct 1: PR out, launch email, GBP posts, first retrofit install scheduled, review engine on | Founder
2.5 POST-LAUNCH 90 DAYS (Oct–Dec)
Month | Focus | Exit criteria
Oct | Deliver founding projects flawlessly; weekly content from real work | 3 projects delivered; 5 reviews; audit pipeline ≥ 8
Nov | Convert audit pipeline; first designer-sourced project | 2 retrofits closed; 5 designers active; CAC data by channel
Dec | Paid media pilot ($2k) on proven message; 2027 plan from real data | 10 lighthouse projects done → Phase 1 gate review (tab 3)

## 3 · Phased Approach
3 · PHASED APPROACH — GATES, NOT DATES
Dates are targets; gates are law. A phase ends only when its exit gates are met. If a gate fails twice, the plan is wrong — revise it, don't force it.
Phase | Window (target) | Theme | Key activities | Investment | EXIT GATES (all required)
Phase 0 — Foundation | Jul–Sep 2026 | Legal, capital, assets, pipeline | Everything in the Workback (tab 2): entity, insurance, licensing path, SBA app, Vela samples, founding-client recruitment, designer outreach | ≈$45k (setup portion of startup budget) | Insurance bound · EC sub signed · funding approved or bank-balance runway ≥9 mo · 6 founding projects signed · site live on real domain
Phase 1 — Proof | Oct 2026–Mar 2027 | 10 lighthouse projects, case-study engine | Deliver founding projects at cost-plus; 20 commercial audits; publish 8+ case studies; 8 founding designers; paid media pilot; service plans attached to every turnkey job | ≈$35k ops + marketing pilot | 10 projects delivered · ≥15 reviews at 4.8+ · blended GM ≥40% · CAC known per channel · 2 designer-sourced projects · cash ≥ plan
Phase 2 — Traction | Apr–Dec 2027 | Repeatable revenue machine | Hire journeyman + bench tech; retrofit becomes 50%+ of revenue; Vela attaches to every project; raise prices 10–15% off proof; scale winning ad channels; 15 active designers | Funded by operations + remaining SBA | $70k+/mo revenue for 3 consecutive months · GM ≥45% · founder <25% time on delivery · service base ≥30 contracts
Phase 3 — Scale | 2028 | Second metro via network + Vela trade sales | Designer-led expansion (no office): 5+ designers in metro #2 with local EC subs; Vela sold to non-project trade (reps/distribution); coordinator + crew #2; consider 504 loan for facility purchase | New capital decision point (LOC/504/retained earnings) | Metro #2 ≥$25k/mo · Vela third-party ≥15% of product revenue · EBITDA ≥15%
Phase 4 — Platform | 2029+ | Optionality | Choose deliberately: (a) regional dominance + cash cow; (b) Vela spinout as product company; (c) franchise/license the model + software to other operators; (d) strategic sale (the About-page thesis: integrated platform + product line + network = attractive acquisition) | Depends on path | Owner's call — the business supports all four
PHASE-GATE REVIEW RITUAL
Last Friday of each phase-end month: score every gate red/green with evidence (numbers from the Forecast tab actuals column). Two reds = phase extends one quarter and ONE root cause gets fixed. Never carry more than one red into a new phase.

## 4 · Revenue Engine
4 · REVENUE ENGINE — HOW EVERY DOLLAR IS MADE
4.1 SIX REVENUE STREAMS — UNIT ECONOMICS
Stream | Avg ticket | COGS | Gross margin | Sales cycle | Volume lever | Notes
1. Turnkey LED retrofit | $28,000 | Kits+labor+disposal ≈ 58% | ≈42% | 3–8 wks (audit→close) | Audits booked/mo | Rebates improve CLIENT math, not our margin — we also charge $350–500 rebate filing (often waived to close)
2. Restoration & chandelier repair | $2,800 | Parts+plating+bench hrs ≈ 40% | ≈60% | 1–3 wks | Bench capacity; ship-in commissions are unbounded by geography | Highest margin + highest brand value; photograph everything
3. Custom fixtures | $7,500 | Fabrication partners ≈ 55% | ≈45% | 4–10 wks | Designer relationships | 50% deposit funds the build — negative working capital
4. Vela Series product | $1,800/order | ODM landed ≈ 45–55% | ≈45–55% | 0–4 wks | Spec attach rate; trade accounts | Internal projects yr 1; third-party trade sales yr 2+ is the equity story
5. Service plans | $588/yr equiv | Truck time ≈ 30% | ≈70% | Attached at sale | Installed base | Included in turnkey price (priced in!); standalone $29–99/mo for non-turnkey clients
6. Design fees & audits | $150–$500 | Founder time | ≈90% | Days | AI Studio volume | Credited to projects — a filter that pays for itself
4.2 PRICING STRATEGY
Value-based, never cost-plus (except founding clients, deliberately). Retrofit priced against the CLIENT's savings: target ≤30-month payback for them, which supports our 42%+ margin. Restoration priced per documented assessment — the dossier justifies the invoice. Custom priced by statement value, floor at 45% GM. Raise prices 10–15% at Phase 2 entry; proof removes price sensitivity.
Optional retrofit closer for hesitant SMBs: shared-savings pilot (we finance one zone, split verified savings 50/50 for 24 mo) — use sparingly, max 1 active pilot, it's a sales tool not a business model.
4.3 LTV / CAC BY SEGMENT
Segment | First ticket GM | Expansion path | 3-yr LTV (GM) | CAC ceiling (payback ≤ 1st project)
Heritage Homeowner | $1,700 | 2nd fixture · relamp sets · referrals (avg 1.3) | ≈$4,200 | $450
Design-Led Renovator | $3,400 | Whole-home phases · service plan · designer referral loop | ≈$8,000 | $450
SMB Retrofit | $11,800 | 2nd building · controls upgrade · service base · referrals | ≈$21,000 | $1,200
Hospitality | $9,000 | Location #2+ · seasonal re-lamping · scene updates | ≈$19,000 | $1,500
Trade partner | $2,500/proj | Every future project they spec | ≈$15,000+ | $800 (recruiting cost)
4.4 CASH MODEL — WHY THIS BUSINESS IS CASH-FRIENDLY
Made-to-order + 50% deposits = we hold client cash before we owe suppliers. Retrofit: 50/40/10 (deposit/delivery/completion). Custom: 50/50. Restoration: assessment fee upfront + 50% on quote approval. Vela stock is the ONLY inventory risk — cap initial stock at $12k and reorder against backlog.
Discipline: 13-week rolling cash forecast every Monday; deposits are project cash, not payroll — track WIP liability explicitly in QuickBooks.
4.5 MARGIN WATERFALL TARGET (steady state, Phase 2)
Line | % of revenue
Blended COGS | ≈54%
Gross margin | ≈46%
Marketing | 8–10%
Ops/facility/insurance/software | 10–12%
Payroll (non-COGS) | 12–15%
EBITDA target | 12–16%

## 5 · Forecast
5 · 36-MONTH FORECAST — EDIT THE YELLOW CELLS; EVERYTHING RECALCULATES
Base case. Yellow = your assumptions (tickets, margins, volumes, opex, funding). Formulas do the rest. Y3 column = Year-2 total × growth factor.
ASSUMPTIONS — UNIT ECONOMICS
Avg retrofit project ($) | 22000 |  | Avg GM % | 42%
Avg restoration ($) | 2800 |  | Avg GM % | 60%
Avg custom fixture ($) | 7500 |  | Avg GM % | 45%
Avg Vela order ($) | 1800 |  | Avg GM % | 50%
Service plan ($/contract/mo) | 49 |  | Avg GM % | 70%
Avg design/audit fee ($) | 300 |  | Avg GM % | 90%
Year-3 growth factor (× Y2) | 1.6
MONTHLY MODEL | Y1 total | Jul '26 | Aug '26 | Sep '26 | Oct '26 | Nov '26 | Dec '26 | Jan '27 | Feb '27 | Mar '27 | Apr '27 | May '27 | Jun '27 | Jul '27 | Aug '27 | Sep '27 | Oct '27 | Nov '27 | Dec '27 | Jan '28 | Feb '28 | Mar '28 | Apr '28 | May '28 | Jun '28 | Year 3
Retrofit projects closed |  | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3
Restorations completed |  | 0 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 7 | 7
Custom fixtures delivered |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Vela orders |  | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7
NEW service contracts |  | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3
Design consults/audits (paid) |  | 2 | 3 | 4 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 12 | 12 | 12 | 12
Service contracts (cumulative)
REVENUE
Retrofit revenue
Restoration revenue
Custom fixture revenue
Vela product revenue
Service plan revenue
Design/audit fees
TOTAL REVENUE
GROSS MARGIN
Retrofit GM
Restoration GM
Custom GM
Vela GM
Service GM
Fees GM
TOTAL GROSS MARGIN
GM %
OPERATING EXPENSES (editable)
Marketing |  | 500 | 500 | 500 | 2500 | 2500 | 2500 | 2500 | 3000 | 3000 | 4000 | 4000 | 4000 | 4500 | 4500 | 5000 | 5000 | 5000 | 5500 | 5500 | 5500 | 6000 | 6000 | 6000 | 6000
Owner draw |  | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000
Staff payroll (non-COGS) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 9500 | 9500 | 9500 | 9500 | 9500 | 14000 | 14000 | 14000 | 14000 | 14000
Facility + storage |  | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
Insurance |  | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900
Vehicle (loan+fuel+maint) |  | 0 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 700 | 700 | 700 | 700 | 700 | 700 | 700 | 700 | 700 | 700 | 700 | 700
Software/office/other |  | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750
ONE-TIME setup costs |  | 12000 | 14000 | 14000 | 6000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL OPEX
CASH VIEW
Operating profit (GM − opex)
Funding inflows (owner/SBA/etc.) |  | 18500 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CUMULATIVE CASH
SCENARIOS — HOW TO STRESS THIS MODEL
• Downside: cut every volume row 40% and delay the 7(a) row to $0 — cumulative cash must stay >$0. If not, cut the M9 hire and owner draw first (they're yellow for a reason).
• Upside: retrofit ramp +50% forces the journeyman hire 3 months earlier — check payroll row before celebrating.
• Rule: re-forecast on the 1st of every month with actuals; variance >20% on any stream two months running = strategy conversation, not a spreadsheet fix.

## 6 · Designer Network
6 · DESIGNER NETWORK PLAN — THE SUPPLY SIDE
The network solves geography and licensing without payroll, and turns the AI Studio into a two-sided funnel. Concierge-first (hand-matched), honest about being new. Site infrastructure already live: /designers page, referral + application pipelines in Supabase.
6.1 VALUE EXCHANGE
Designers give us | We give designers
Local delivery capacity in their metro | Qualified, pre-scoped leads (room, fixture direction, budget band from AI Studio) — free during founding period
Spec loyalty to Vela + catalog | Trade pricing: 25% off list (we retain ~15–20% margin)
Case studies + co-branded content | Fabrication + restoration bench behind their designs
A referral fee on projects we source later (10%, post-founding) | Retrofit program support: audits, financial analysis, rebate filing under their brand if desired
6.2 RECRUITING FUNNEL — 8 FOUNDING MEMBERS BY DEC 2026
Stage | Target # | How
Prospect list | 50 | IALD + ALA member directories · IES local section rosters · Instagram/Houzz search ('lighting designer <metro>') · showroom staff going independent
Personal outreach | 50 | Individual notes referencing THEIR work (never blast); offer: founding member, zero fees, shape the terms
Discovery calls | 20 | 30 min: their pipeline, their gaps, our support menu
Applications | 12 | Via /designers form (portfolio, region, specialties)
Vetted + signed | 8 | Rubric below + founding-member agreement
6.3 VETTING RUBRIC (score 1–5 each; ≥18 to join; no 1s)
Criterion | What good looks like
Portfolio quality | Layered light, warm palettes, glare discipline — our aesthetic language
References | 2 client + 1 contractor reference, called personally
Professionalism | Responds inside 2 business days; carries insurance; contracts in writing
Coverage & capacity | Serves a definable metro; can take ≥2 projects/quarter
Values fit | Comfortable with honest claims culture; no spec-and-disappear artists
6.4 FOUNDING MEMBER TERMS (v1 — refine with first 3 signees)
Term | 12 months, renewable; either party exits with 30 days notice, active projects protected
Fees | Zero platform fees during founding period; leads we send are free; post-founding: 10% referral on Lumenwright-sourced project design fees
Product | 25% trade discount; Vela spec support incl. photometrics; NET-15 after first 3 orders
Standards | 1-business-day response SLA to intros; client survey after each project; co-marketing rights (both ways, approval required)
Exclusivity | None — but 'Founding Member' badge is limited to 10, ever
6.5 ENABLEMENT KIT (ship within 1 week of signing)
Welcome box: Vela Linea + Punto samples, candelabra warm-dim set, finish chips · Spec binder (cut sheets, IES files) · Co-branded audit one-pager · Directory profile live on /designers · Intro to their local EC sub where we have one
6.6 NETWORK SCORECARD (monthly)
Metric | Target
Intro → response within SLA | 100%
Intro → project conversion | ≥30%
Client satisfaction (post-project survey) | ≥4.7/5
Designer product orders/quarter | ≥1 per active member
Designer NPS | ≥60
6.7 EXPANSION RULE
Open metro #2 only when: 3+ vetted applicants there + 10+ organic AI-plan leads/month from that metro + one anchor designer willing to co-launch. Network-led expansion costs ≈$3k (travel + enablement kits), not an office.

## 7 · Digital Marketing
7 · DIGITAL MARKETING PLAN + SOCIAL STRATEGY
7.1 BRAND PILLARS (every piece of content maps to one)
Pillar | Story | Proof format
Resurrection | Dead heirlooms brought back to light | Before/after restorations, process video
Craft | How light is actually made — bench, brass, glass, dimming curves | Macro shots, 'why warm-dim matters' explainers
Savings with taste | LED conversion that doesn't look like an office supply store | Retrofit case studies with kWh + design photos
The machine | AI reads your room; a human designs it | Screen-capture demos, plan→reality reveals
7.2 SEO — WHERE THE BUYING INTENT ALREADY IS
Cluster | Example keywords | Page | Priority
Restoration (local) | chandelier repair near me · antique light restoration <metro> · rewire old chandelier | Service pages + metro landing pages | P0 — demand exists, supply is weak
Retrofit (commercial) | led retrofit <metro> · fluorescent to led conversion cost · commercial lighting rebates <state> | Retrofit page + ROI calculator (already built — a natural link magnet) | P0
Vintage knowledge | how to date an antique chandelier · are old chandeliers safe · sputnik chandelier history | Blog/guides — top-funnel authority | P1
Product | warm dim candelabra led · plaster-in led channel · 2 inch trimless downlight | Product pages (already indexed-ready) | P1
Local moves: Google Business Profile with weekly photo posts (restorations are catnip); top-20 citations; review velocity (ask on delivery day, QR card in every crate); one metro landing page per service.
7.3 CONTENT ENGINE — ONE RESTORATION FEEDS EVERYTHING
Every project is filmed. One restoration yields: 1 long-form YouTube (8–15 min process film) → 4–6 vertical clips (Reels/TikTok/Shorts) → 1 before/after carousel → 1 case-study page → 1 email → GBP posts. Batch production day: every other Friday. The niche precedent is proven — restoration/repair channels routinely build 100k+ audiences from bench footage; nobody owns 'chandelier surgeon' yet.
7.4 SOCIAL STRATEGY BY PLATFORM
Platform | Role | Format | Cadence | 12-mo KPI
Instagram | Portfolio + designer credibility (trade watches here) | Before/after carousels · process Reels · Stories from the bench | 4 posts + 3 Reels/wk | 8k followers · 50 designer DMs · top referral source for custom
TikTok | Reach + the 'oddly satisfying' restoration audience | Crystal cleaning, rewiring, first-light moments, ember-flicker demos | 3–5 clips/wk (reposts fine) | 1 breakout (>500k views) · 15k followers
YouTube | Trust + search ('how to' + process films) | Long-form restorations · retrofit case walkthroughs · dimming science | 2/mo long-form + Shorts | 5k subs · ranks for 'chandelier restoration'
Pinterest | Renovation planners (12–18 mo intent) | Finished rooms, fixture boards by style | 10 pins/wk (scheduled) | Steady referral traffic to product pages
LinkedIn | Commercial retrofit + acquisition-side credibility | Case studies w/ kWh math · rebate deadline alerts · founder build-in-public | 2/wk | 20 audit requests sourced
Facebook/Nextdoor | Local homeowners + estate/antique groups | GBP cross-posts; genuinely helpful answers in antique groups (no pitching) | 2/wk + group participation | Local referral flywheel
7.5 PAID MEDIA (starts M4, AFTER 5 case studies)
Channel | Budget start → scale | Target | Kill rule
Google Local Services Ads | $800/mo → $2k | 'Chandelier repair' + 'lighting installation' — pay per lead | CPL > $80 for 3 wks
Google Search (exact clusters) | $1,200/mo → $4k | Retrofit + restoration intent terms; LP = audit booking / restoration intake | CAC > segment ceiling (tab 4)
Meta retargeting | $400/mo | AI-plan users + site visitors → consult booking | ROAS < 3 after 60 days
Meta prospecting | $0 until Phase 2 | Lookalikes of consult bookers; creative = restoration video | Never scale before retargeting works
7.6 EMAIL — THE AI-PLAN FOLLOW-UP (already capturing via Supabase)
Day | Email | Job
0 | Your lighting plan (PDF render of the AI plan) | Deliver value; set consult CTA
2 | The one mistake in most <room> lighting | Teach; build authority
5 | What this looks like in real homes (case study) | Proof
9 | What it costs (honest ranges + payback) | Qualify; kill price anxiety
14 | 20-minute designer review — calendar link | Convert; last touch before monthly digest
Also: monthly 'From the Bench' digest (1 restoration, 1 tip, 1 open slot) — the long-cycle nurture for 12-month renovators.
7.7 BUDGET + FUNNEL TARGETS
Period | Monthly budget | Expected leads | Consults | Projects | Blended CAC check
M1–3 (organic+founding) | $500 (tools/boosts) | 30 | 12 | 6 (founding) | n/a — proof phase
M4–6 (paid pilot) | $2,500 | 60 | 18 | 6–8 | ≤$450 res / ≤$1,200 comm
M7–12 (scale winners) | $4,000–6,000 | 100+ | 30 | 10–14 | Same ceilings; kill losers monthly
7.8 12-WEEK LAUNCH SOCIAL CALENDAR (repeatable skeleton)
Week | Hero content | Supporting posts
1 | Launch film: 'Why we bring dead light back' | Founder intro · bench tour · GBP launch post
2 | Restoration #1 long-form (YouTube) | 3 clips · before/after carousel · dossier close-up
3 | AI Studio demo (photo → plan in 60s) | Plan→reality split-screens · 'what the AI saw'
4 | Retrofit case: '<Client> cut lighting energy 58%' | kWh math explainer · rebate deadline PSA (LinkedIn)
5–12 | Alternate: restoration film / retrofit case / craft explainer / designer feature | Each hero → 4–6 cutdowns + 1 email + GBP; feature one founding designer/mo (their audience becomes yours)

## 8 · Vendors + Sourcing
8 · VENDORS + SOURCING — WHO MAKES EVERYTHING
Rule: two qualified sources per critical category before Phase 2. Named companies below are established, well-known suppliers to start diligence with — verify current terms directly; this is a sourcing map, not an endorsement list.
8.1 SOURCING MAP BY CATEGORY
Category | What | Where to source (start here) | Terms to target
LED engines & drivers | COBs, modules, drivers for custom builds + Vela | Drivers: Mean Well, Inventronics · COB/modules: Bridgelux, Citizen, Samsung LED · via distributors: Future Electronics, Arrow, DigiKey for protos | Distributor accounts; datasheet + LM-80 on file for everything installed
Retrofit kits & lamps (resale) | DLC-listed troffer kits, UFO high bays, track heads, warm-dim candelabra | Search DLC Qualified Products List (designlights.org) then buy through electrical distribution: Rexel, CED, Graybar, City Electric · known retrofit brands to price: Keystone Technologies, Espen Technology, EarthTronics, RAB, Sylvania/LEDVANCE | Contractor pricing account + NET-30; DLC listing verified per SKU (rebate eligibility!)
Vela Series ODM | Linea channel, Punto downlight, Arco cove, Firma grazer, Scena controls | Route A (speed): white-label from Alibaba Verified/Trade Assurance suppliers (search 'plaster-in aluminum profile LED', 'trimless 2 inch downlight') · Route B (quality): Taiwan/Korea ODMs via Taipei Int'l Lighting Show · Route C (US assembly): extrusions imported, boards + assembly domestic for 'assembled in USA' spec story | Samples first, always · LM-79/LM-80 test reports · 30/70 payment (30% PO, 70% after 3rd-party inspection) · NNN agreement (not just NDA) for custom tooling · QIMA or SGS inspection every production PO
Restoration parts | Sockets, cloth wire, arms, canopies, crystal, glass | Grand Brass Lamp Parts (NY) · B&P Lamp Supply (TN, trade account) · crystal: import replacements via European/Egyptian crystal houses, match-service from strung samples · custom glass: local glassblowing studios (find via craft guilds + art schools) | Trade accounts at both majors (resale cert required); keep a $2–3k parts library of the 50 most-used pieces
Antique fixture inventory | One-of-ones for the Vintage collection | Estate sales (EstateSales.net alerts) · architectural salvage: Olde Good Things and regional salvage yards · auctions: LiveAuctioneers/local auction houses · demolition contractors (call them — they throw chandeliers away) · 'we buy broken chandeliers' page on our own site | Buy at ≤15% of expected restored retail; document provenance at purchase
Custom fabrication | Machining, spinning, casting, powder coat, plating | ThomasNet/Xometry for machined + sheet parts · local metal spinners + powder coaters (audit in person) · plating: regional job shops (nickel/brass) — restoration-grade matters | 2 shops per process; prototype tolerance agreement before first client job
Controls ecosystem | Dimmers, wireless, DALI, keypads | Lutron (residential + commercial programs) · Casambi partner program (wireless) · DALI-2 components via distribution | Join Lutron/Casambi pro programs early — training + demo gear + spec listing
Crating & freight | Insured fixture transport (ship-in restorations!) | Custom crating: local crate shops or build in-house (jig on Ops list) · freight: FedEx Freight/regional LTL + Craters & Freighters for white-glove | Declared-value insurance ALWAYS; photo protocol at pack + unpack
Lamp/ballast recycling | Compliance disposal for retrofits | National mail-back/box programs and regional universal-waste recyclers (search state environmental agency's approved list) | Keep manifests 3 yrs; show clients the certificate — it sells
8.2 TRADE SHOWS & SOURCING CALENDAR
Event | When/where (verify dates) | Go for
LEDucation | Mar · NYC | Architectural LED suppliers, controls, cheap to attend — best first show
LightFair | Rotates (major US lighting show) | Retrofit OEMs, DLC vendors, rep relationships
Light + Building | Frankfurt · biennial (even yrs) | Design direction + European component sources — Phase 3 trip
Hong Kong Int'l Lighting Fair | Oct · HK | ODM speed-dating for Vela — bring the spec book
High Point Market | Apr + Oct · NC | Where interior designers shop — sell side, not buy side
8.3 VENDOR VETTING CHECKLIST (any vendor > $5k/yr)
□ Business verified (registry/D&B or Alibaba Verified+years) □ 3 references or review history □ Sample evaluated on OUR test rig (dimmer wall, CCT meter) □ Test reports where applicable (LM-79/LM-80, UL/ETL cert numbers verified on UL database) □ Written lead times + late-delivery remedy □ Payment terms in writing □ Second source identified □ For ODM: NNN signed, tooling ownership stated, inspection rights in PO
8.4 MADE-TO-ORDER FULFILLMENT FLOW (matches the Supabase order pipeline)
Step | Actor | System state (order_requests.status)
Client configures + requests order | Site | new
We confirm options/price/lead time; take 50% deposit | Founder | confirmed
PO to manufacturer/fabricator with spec pack | Founder | sent_to_manufacturer
Inspection (photos or 3rd-party for Vela POs) → ship/crate | Vendor + us | sent_to_manufacturer
Delivery/install + commissioning; balance collected; service record opened | Us/EC sub | fulfilled

## 9 · Funding + Startup
9 · FUNDING STACK — SBA + COMPLEMENTS, AND STARTUP COSTS
9.1 STARTUP COSTS (one-time + first-6-months runway)
Category | Item | Amount
Legal & compliance | LLC/registrations, contracts drafted (founding client, sub agreement, network terms), state filings | 3500
Insurance | GL + products/completed-ops + inland marine + commercial auto (6 mo premiums) | 5500
Licensing path | EC sub onboarding, permits float, owner course/exam fees | 2500
Workshop equipment | Restoration bench, rewiring tools, dimmer test wall, CCT/flicker meter, crating jig | 9500
Vehicle | Used cargo van + wrap + shelving | 21000
Vela launch stock | Samples + first production PO (capped) | 12000
Restoration parts library | Top-50 parts stock (Grand Brass/B&P opening orders) | 2500
Brand & site | Domain, email, photography kit (used FF camera + lights), print (audit one-pagers, crate QR cards) | 3000
Marketing launch | M1–6 budget incl. paid pilot (tab 7) | 9000
Software/ops | QuickBooks, field app, scheduling, misc SaaS (6 mo) | 1500
Trade shows/sourcing | LEDucation trip + ODM sample costs | 3000
Working capital reserve | 6 mo fixed costs buffer (the 'sleep at night' line) | 40500
Contingency | 10% of above | 5000
TOTAL |  | 118500
9.2 THE FUNDING STACK (recommended sequence)
Layer | Amount | Source | Terms (typical — verify current) | When
1. Owner injection | $18,500 | Personal savings | Equity — lenders want to see ~10–15% skin | Now
2. SBA Microloan | $50,000 | Nonprofit intermediary/CDFI (find via SBA Lender Match) | ≤$50k · ~8–13% · ≤7 yrs · faster + startup-friendly + free TA coaching | Apply Jul, fund by Sep
3. Equipment financing | $21,000 | Bank/credit union or dealer | Van as collateral · 6–9% · 5 yrs · preserves cash vs buying outright | At purchase (Aug)
4. SBA 7(a) Small | $75,000–150,000 | SBA-preferred bank (community banks, Live Oak-style SBA specialists, Huntington) | Prime + ~2.75–4.75% · ≤10 yrs working capital · personal guarantee + likely blanket lien | Apply M4–6 WITH TRACTION (founding projects + this workbook + actuals) — approval odds and terms improve dramatically
5. SBA CAPLine / bank LOC | $25,000–50,000 | Same lender as 7(a) | Revolving; for retrofit WIP timing gaps | Secure in M6–9 BEFORE it's needed
Later: SBA 504 | TBD | CDC + bank | Owner-occupied facility purchase, ~10% down, long fixed | Phase 3 if buying the shop
Why staged: microloan now funds launch without betting everything on one approval; the 7(a) lands after 3–6 months of real revenue, which converts you from 'idea borrower' (hard) to 'traction borrower' (routine).
9.3 NON-DEBT COMPLEMENTS
Source | Fit | Notes
Customer deposits | Core — negative working capital by design | 50% deposits are the cheapest financing that exists
Vendor terms | NET-30/60 at distributors after 2–3 orders | Ask at every account opening; it's free float
Utility on-bill financing / C-PACE | Finances the CLIENT's retrofit, not us | Closes deals without us carrying paper — learn local programs in Phase 0
State/utility efficiency grants | Occasional small-biz energy grants | Check state energy office + utility trade-ally programs; also register as a trade ally (lead source!)
Revenue-based financing / Stripe Capital | Phase 2+, only against proven margin | Expensive; use for inventory turns, never payroll
Angels/strategic | Only for the Vela spinout thesis (Phase 4) | Don't sell equity to fund a services launch that debt covers
9.4 LENDER READINESS CHECKLIST
□ This workbook (plan + forecast) □ Personal financial statement + 3 yrs personal returns □ Credit ≥680 (check + fix now) □ Owner injection documented (bank stmts) □ Entity docs, EIN, licenses/insurance certs □ Use-of-funds table (9.1) □ Collateral schedule (van, equipment, blanket lien expectation) □ DSCR story: forecast shows ≥1.25 coverage by M12 □ 2-min pitch: what, who pays, why you, why now □ Apply to 3 lenders in parallel — terms vary wildly
9.5 USE-OF-FUNDS TIMELINE
Month | Deployed | Purpose
Jul–Aug | $38k | Setup: legal, insurance, equipment, van (financed), samples, brand
Sep–Oct | $25k | Vela stock, parts library, launch marketing, working capital begins
Nov–Mar | $45k | Runway coverage while founding projects convert to full-price pipeline; paid media pilot
Reserve | $10k+ | Untouched contingency — replenish before growth spending